## COCOMO
Basic
cocomo
Organic
[6 empty] | Size= | 1 | KLOC | Calculations
[6 empty] | A= | 2.4 |  | E= | 3.6223 | staff-month | Effort
[6 empty] | B= | 1.05 |  | D= | 4.0771 | months | Dev Time
| very low | low | nominal | very high | extra high | C= | 2.5 |  | SS= | 0.88845 | staff | Number of developers
PCAP | 1.42 | 1.17 | 1 | 0.86 | 0.7 | D= | 0.38 |  | P= | 0.27607 | KLOC/PM | Productivity
[6 empty] | AEXP | 1.29 | VERY LOW | EAF= | 1.5093 |  | Aplication Erxperience
[6 empty] | LEXP | 1 | NOMINAL |  |  |  | Programming languaje exp
[6 empty] | PCAP | 1.17 | LOW |  |  |  | Programming Capability
Semidetached
[6 empty] | Size= | 200 |  | Calculations
[6 empty] | A= | 3 |  | E= | 1133.1172 | staff-month
[6 empty] | B= | 1.12 |  | D= | 29.3046 | months
[6 empty] | C= | 2.5 |  | SS= | 38.6668 | staff
[6 empty] | D= | 0.35 |  | P= | 0.1765 | KLOC/PM
Embedded
[6 empty] | Size= | 400 |  | Calculations
[6 empty] | A= | 3.6 |  | E= | 5849.0833 | staff-month
[6 empty] | B= | 1.2 |  | D= | 40.1244 | months
[6 empty] | C= | 2.5 |  | SS= | 145.7739 | staff
[6 empty] | D= | 0.32 |  | P= | 0.068387 | KLOC/PM
[6 empty] | AEXP | 1.29 |  | EAF= | 1.2255
[6 empty] | LEXP | 0.95
Effort(E) = ab * (KLOC)^bb(in Person-months)
DevelopmentTime(D) = cb * (E)^db (in month)
Average staff size(SS) = E/D (in Person)
Productivity(P) = KLOC / E (in KLOC/Person-month)

## FP
Complexity point table
|  | Simple | Average | Complex
Inputs |  | 2 | 4 | 6
Outputs |  | 3 | 5 | 7
Files |  | 5 | 10 | 15
Inquires |  | 2 | 4 | 6
Interfaces |  | 4 | 7 | 10
Example
Inputs |  |  | Weight | FP
| Simple | 1 | 2 | 2 | user request for inventory information | Variable Adjustment Factor
| Average | 0 | 4 | 0
| Complex | 0 | 6 | 0 |  | Complex Internal Processing | 4
Outputs | [5 empty] | Code to be reusable | 0
| Simple | 1 | 3 | 3 | results of the user's query
| Average | 0 | 5 | 0 |  | High performance | 1
| Complex | 0 | 7 | 0 |  | Multiple sites | 1
Files | [5 empty] | Distributed processing | 0
| Simple | 4 | 5 | 20 | 4 database accesses, to insert, delete and query (2) | Project Adjustment Factor | 6
Inquiries
| Simple | 1 | 2 | 2 | processing of the query
Interfaces | [5 empty] | Adjustment calculation
| Simple | 2 | 4 | 8 | Scanner readings to enter and delete in the inventory
| Average | 0 | 7 | 0 |  | Adjustment FP = Unajusted FP x [0.65 +(adjustment factor X 0.01)]
[6 empty] | Adjusted FP = | 24.85
|  |  |  | 35 | Unadjusted function points
Impact of fucntion points depend on organizations previous experience, for example:
By experience a programmer averages 18 funtion points per month
197 divided by 18
10.9444 | man - months
Average programmer salary = 5200 per month
11 man-months x 5200 =
57200
A tracking system for beer warehouse inventory keeps track of what good are stored in a warehouse. As boxes of beer enter the warehouse, bar codes on the boxes that identify their contents are scanned and a record for each box is entered into a database of stored merchandise. As boxes leave the warehouse, their bar codes are scanned again by a different reader in order to remove them from the database. The bar code indicates the kind of beer and kind of container to be found in the box; a table of codes and meanings determines the correspondence between code and box contents. A user can query the inventory database for the presence or absence of particular kinds of boxes in the warehouse, Base upon the description calculate the function points of this project.

## OP
Screens |  |  |  |  | Reports
| # sources of data tables |  |  |  |  | # sources of data tables
#Views | Total <4 (<2 serves <3 clients) | Total < 8 (2/3 servers 3-5 clients | Total 8+ (>3 servers >5 clients |  | #of sections contained | Total <4 (<2 serves <3 clients) | Total < 8 (2/3 servers 3-5 clients | Total 8+ (>3 servers >5 clients
<3 | simple | simple | medium |  | 0 or 1 | simple | simple | medium
3 to 7 | simple | medium | difficult |  | 2 or 3 | simple | medium | difficult
>8 | medium | difficult | difficult |  | 4+ | medium | difficult | difficult
Weight |  |  |  |  | Productivity
Type | Simple | Medium | Difficult |  | Developer experience |  | Very low | low | nominal | high | very high
Screen | 1 | 2 | 3 |  | Productivity |  | 4 | 7 | 13 | 25 | 50
Report | 2 | 5 | 7 |  | CASE capability |  | 4 | 7 | 13 | 25 | 50
Modules (3GL component) |  |  | 10
Effort = | NOP /Productivity
NOP = | OP ((100-%reuse)/100)
Example
Name | Objects | Comp | Weight
Booking | Screen | Simple | 1
Pricing | Screen | Simple | 1
Availability | Screen | Medium | 2
Sales | Report | Medium | 5
|  | Total | 9 | OP
Developers experience |  | very LOW | 4
CASE capability |  | LOW | 7 |  | Average | 5.5
NOP | 9
Effort | 1.6364 | man monthns
Application will have 3 screens and will produce 1 report: – A booking screen: records a new sale booking – A pricing screen: shows the rate for each day and each flight – An availability screen: shows available flights – A sales report: shows total sale figures for the month and year, and compares figures with previous months and years
Booking screen: – Needs 3 data tables (customer info, customer history table, available seats) – Only 1 view of the screen is enough. So, the booking screen is classified as simple. ■ Similarly, the levels of difficulty of the pricing screen, the availability screen and the sales report are classified as simple, simple and medium, respectively. There is no 3GL component.