## Product backlog
1. Guest
1.1. Can access the current sensor data through 3 elements:
1.1.1. Current global data: indicates the average values of the last hour of all sensors concerning temperature, humidity, PM 2.5 and PM 10.
1.1.2. Graphs: Indicates the average values of all sensors concerning temperature, humidity, PM 2.5 and PM 10, these can be specified in time periods and grouped by:
1.1.2.1. Daily: Hourly average.
1.1.2.2. Weekly: Daily average
1.1.2.3. Monthly: Weekly average
1.1.2.4. Annual: Monthly average
1.1.3. Map: Indicates separately the values of each sensor, pressing on the marks of each sensor shows the measurements registered by that sensor, these can be specified in periods of time and grouped by:
1.1.3.1. Daily: Hourly average.
1.1.3.2. Weekly: Daily average
1.1.3.3. Monthly: Weekly average
1.1.3.4. Annual: Monthly average
2. Researchers:
2.1. Signed access to the system
2.1.1. Can register as a researcher with a user name and password, as well as your profile.
2.1.2. Can modify your profile.
2.1.3. Can change your password.
2.2. Can access the current sensor data by means of 3 elements:
2.2.1. Current global data: shows the average values of the last hour of all sensors concerning temperature, humidity, PM 2.5 and PM 10 2.2.2.
2.2.2. Graphs: Indicates the average values of all sensors concerning temperature, humidity, PM 2.5 and PM 10, these can be specified in time periods and grouped by:
2.2.2.1. Daily: Hourly average.
2.2.2.2.2. Weekly: Daily average
2.2.2.3. Monthly: Weekly average
2.2.2.4. Annual: Monthly average
2.2.3. Map: Indicates separately the values of each sensor, pressing on the marks of each sensor shows the measurements registered by that sensor, these can be specified in periods of time and grouped by:
2.2.3.1. Daily: Average per hour
2.2.3.2. Weekly: Daily average
2.2.3.5. Monthly: Weekly average
2.2.3.4. Annual: Monthly average
2.3. Sensors
2.3.1. Can view in tabular form the data of a sensor within a set period of time.
2.3.2. Can download in a file the data of a specific sensor within a set period of time.
2.3.3. Can view in graphical form the data of a specific sensor within a set period of time.
3. Administrator:
3.1. User control
3.1.1. Can register as a researcher with a user name and password, as well as your profile.
3.1.2. Can modify your profile.
3.1.3. Can change your password.
3.1.4. Can change the password of a researcher.
3.1.5. Can create and delete researcher's accounts
3.2. Can access the current sensor data by means of 3 elements:
3.2.1. Current global data: indicates the last hour's average values of all sensors concerning temperature, humidity, PM 2.5 and PM 10 3.2.2.
3.2.2. Graphs: Indicates the average values of all sensors concerning temperature, humidity, PM 2.5 and PM 10, these can be specified in time periods and grouped by:
3.2.2.1. Daily: Hourly average
3.2.2.2. Weekly: Daily average
3.2.2.4. Monthly: Weekly average
3.2.2.5. Annual: Monthly average
3.2.3. Map: Indicates separately the values of each sensor, pressing on the marks of each sensor shows the measurements registered by that sensor, these can be specified in periods of time and grouped by:
3.2.3.1. Daily: Hourly average
3.2.3.2. Weekly: Daily average
3.2.3.3. Monthly: Weekly average
3.2.3.4. Annual: Monthly average
3.3. Sensors
3.3.1. Can view in tabular form the data of a sensor within a set period of time.
3.3.2. Can download in a file the data of a specific sensor within a set period of time.
3.3.3. Can view in graphical form the data of a specific sensor within a set period of time.
3.3.4. Can add new sensors.
3.3.5. Can delete sensors
3.3.6. Can activate or deactivate sensors.
3.3.7. Can add or delete which data is being measured on a sensor

## Scrum artifacts
ID | Epic | Story | Estimate | Release | Spring 1 2 weeks | Spring 2 2 weeks | Spring 3 2 weeks | To Do | In Progress | Testing | Done
1 | User administration | Can create and delete user's accounts | 5 | 1 | X
2 |  | Register with a user name and password, as well as your profile. | 5 | 1 | X
3 |  | Modify profile. | 5 | 2 |  | X
4 |  | Modify password | 8 | 2 |  | X
5 | Sensor administration | Add new sensors. admin user only | 5 | 1 | X
6 |  | Activate or deactivate sensors. admin user only | 5 | 2 |  | X
7 |  | Add or delete which data is being measured on a sensor. admin user only | 8 | 2 |  | X
8 |  | Delete sensors admin user only | 2 | 1 | X
9 |  | Reading sensor data and storing it in a database | 10 | 1 | X
10 | Create home page | Reading the database and calculating the average of the last hour of each sensor and display on screen | 10 | 1 | X
11 |  | Screen formatting, and selection of images referring to the values of the measurements | 5 | 1 | X
12 | Data recovery | Data recovery according to the established filters and validating user | 8 | 1 | X
13 |  | Calculation of the averages according to the selected grouping (daily, weekly, monthly or annual) | 12 | 2 |  | X
14 |  | Download the processed information to a file | 12 | 2 |  | X
15 | Generation of graphs and tables | graph generator from the calculated data | 8 | 3 |  |  | X
16 |  | table generator from the calculated data | 8 | 3 |  |  | X
17 | Sensor map generator | Generate a city map | 12 | 3 |  |  | X
18 |  | Create pointers to the areas where there are sensors | 10 | 3 |  |  | X
19 |  | Associate the sensor information with each pointer and display it on the screen | 10 | 3 |  |  | X
148

## Release
Release | Description
1 | Basic portal, create users, sensors. it can read the data of the sensors and generates main screen with the average data of the last hour
2 | Advanced portal, allows you to configure the user profile, configure the sensor, process the data according to the selected periods and download the information in a file
3 | Final portal, presents the selected data through graphs, tables and maps

## Burn Down Chart
BRUDOWN CHART |  | GESTIÓN DIARIA
Start Date | 2021-04-26 | Day | Planned Work | Real Work | Current Value
Finish Date | 2021-05-14 | 1 | 50 | 50 | 0
Total effective working days (ideal time) | 10 | 2 | 46 | 50 | 0
Total de puntos | 50 | 3 | 42 | 50 | 0
Ideal de puntos por día | 4 | 4 | 38 | 50 | 0
|  | 5 | 34 | 45 | 5
Sprint 2 weeks | 10 | 6 | 30 | 45 | 0
Planning Meeting | 0.75 | 7 | 26 | 45 | 0
Review Meeting | 0.375 | 8 | 22 | 45 | 0
Retrospective Meeting | 0.375 | 9 | 18 | 45 | 0
Really effective days | 8.5 | 10 | 14 | 45 | 0
|  | 11 | 10 | 45 | 0
|  | 12 | 6 | 45 | 0
|  | 13 | 2 | 45 | 0
|  | 14 | -2 | 45 | 0